| Wk | Elliott | Lloyd | Oliver | Mitchel | Eric | Thomas |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented | . Begin reading criteria for assessment 3 + 5. Identify individual strengths and where they can be implemented |
| 2 | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission | . Meeting 1: Divide main parts of assessment evenly among group members . Set rough time frame for drafts and final submission |
| 3 | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Begin Ms teams report . Draft - Timeframe section . Draft – Presentation script | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Draft – Tools and Tech | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Draft – Testing . Draft - Risks | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Provide detailed overview of project for team members to work on. . Draft – Aims | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Draft - Plans and Progress . Draft – Career plans | . Meeting 2: Reflect and discuss assessment 2 feedback and marks. . Update personal information . Draft – Presentation . Draft – Roles . Begin to write script. |
| 4 | . Meeting 3: Pulse check and distribute remaining tasks . Presentation recording . Career plans and personal profile . Proofread teams work | . Meeting 3: Pulse check and distribute remaining tasks . Draft – Scope and Limits . Proofread teams work | . Meeting 3: Pulse check and distribute remaining tasks . Draft – Group processes . Proofread teams work | . Meeting 3: Pulse check and distribute remaining tasks . Draft – Overview . Meeting with tutors to discuss assessment 2 . Proofread team’s work | . Meeting 3: Pulse check and distribute remaining tasks . Career plans and personal profile . Second draft Plans and progress . Proofread teams work | . Meeting 3: Pulse check and distribute remaining tasks . Draft complete script for presentation. . Complete presentation intro . Proofread teams work |
| 5. | . Meeting 4: second draft due . Career plans and personal profile . Complete draft – Time frame . Update Tool Attachment . 2nd proofread of team’s work | . Meeting 4: second draft due . Update Website . Career plans and personal profile . 2nd proofread of team’s work | . Meeting 4: second draft due . Career plans and personal profile . Complete all drafts . 2nd proofread of team’s work | . Meeting 4: second draft due . Presentation recording . Complete draft – Overview and aims. . Career plans and personal profile . 2nd proofread of team’s work | . Meeting 4: second draft due . Complete Plans and progress . 2nd proofread of team’s work | . Meeting 4: second draft due . Presentation recording . Presentation editing . 2nd proofread of team’s work |
| 6 | . Meeting 5: Complete final draft edits. . Group Reflection . Submit Report and presentation | . Meeting 5: Complete final draft edits. . Update Website . Group Reflection . Submit Report and presentation | . Meeting 5: Complete final draft edits. . Group Reflection . Submit Report and presentation | . Meeting 5: Complete final draft edits. . Group Reflection . Submit Report and presentation | . Meeting 5: Complete final draft edits. . Group Reflection . Submit Report and presentation | . Meeting 5: Complete final draft edits. . Group Reflection . Submit Report and presentation |
| 7 | . Meeting 6: Discuss expansion of project development . Designate roles . Role: Role: Tech designer . Research role requirements | . Meeting 6: Discuss expansion of project development . Designate roles Role: Web Developer . Research role requirements | . Meeting 6: Discuss expansion of project development . Designate roles Role: User interface design . Research role requirements | . Meeting 6: Discuss expansion of project development . Designate roles Role: Lead Dev . Research role requirements | . Meeting 6: Discuss expansion of project development . Designate roles Role: Financial adviser . Research role requirements | . Meeting 6: Discuss expansion of project development. . Designate roles Role: Marketing . Research role requirements |
| 8 | . Meeting with Oliver and Mitchel to plan program. . Create a budget. . Finance meeting with Eric. | . Create plan. Gather information regarding goals, audience, basic software etc. . Create a budget. . Finance meeting with Eric. | . Meeting with Elliott and Mitchel to plan program. . Create a budget. . Finance meeting with Eric. | . Meeting with Oliver and Elliott to plan program. . Create a budget. . Finance meeting with Eric. | . Discuss with Team members individually on potential costs of their role | . Research target audience . Create a budget. . Finance meeting with Eric. |
| 9 | . Map backend structure and identify potential user caused error. | . Create a wireframe/sitemap . pulse check with Mitch | . Research interface design options. | . Research server options | . Analyse and identify areas where money can be better allocated. | . Produce Survey for potential customers. |
| 10 | . Build basic user settings pathway. . Test and debug. | . Graphical Design (colours, layout, branding, interface). . Implement to wireframe. | . Design user interface in conjunction with Mitch and Elliott. | . Touch base with team members individually . Pulse check | . Research 3rd party companies to help develop our project. | . Survey potential customers online and face to face – on campus, libraries etc. |
| 11 | . Build basic user settings pathway. . Test and debug. | . Present website plan to group . Make any conceptual changes to plan. | . Build user interface . Debug | . Write content for Website i.e., Mission statement, aims, future development etc. | . Gather quotes from suitable companies. | . Survey potential customers online and face to face – on campus, libraries etc. |
| 12 | . Meeting 7 – Pulse check . Build Advance user setting pathway. . Test and debug. | . Meeting 7 – Pulse check . Code HTML for website | . Meeting 7 – Pulse check . Build user interface . Debug . Implement and programs from Elliott’s end | . Meeting 7 – Pulse check . Market research . Customer testing . Website input | . Meeting 7 – Pulse check . Write a fully costed report | . Meeting 7 – Pulse check . Analyse findings . Identify what the customers’ needs and wants when it comes to interface and accessibility. |
| 13 | . Build Advance user setting pathway. . Test and debug. | . Code CSS for website | . Customer Testing . Make any changes | . Touch base with team members individually . Pulse check . Identify problem areas | . Present report to team and discuss any changes. . Make necessary changes | . Write report for team to help them build on their individual roles. |
| 14 | . Marketing meeting with Thomas. . Implement suggested changes (if any) from Thomas. . Test and debug. | . Website testing. . Stress test . Marketing meeting with Thomas | . Marketing meeting with Thomas . Testing | . Write Business plan with Eric . Marketing meeting with Thomas . Write terms and conditions. | . Write Business plan with Mitchel . Marketing meeting with Thomas | . Present report to team . One on one meetings with team members. |
| 15 | . Present program to team for testing. . Write report on progress | . Launch and maintain Website . Write report on progress | . Debug and patch . Write report on progress | . Approach potential investors . Write report on progress | . Approach potential investors . Write report on progress | . Build online profile and Networking . Write report on progress |
| 16 | . Final Meeting . Present report and discuss future | . Final Meeting . Present report and discuss future | . Final Meeting . Present report and discuss future | . Final Meeting . Present report and discuss future | . Final Meeting . Present report and discuss future | . Final Meeting . Present report and discuss future |

The first six weeks of the following table represent what our group has achieved on an individual level.  Based off our workloads for those weeks, we were able to make what we think, is a fairly accurate prediction on what we could achieved if we had an extra ten weeks to work on our project.  The later stages of this plan are assuming we are able to maintain an average of ten hours work per week.  The nature of a project like this may lead to unforeseen hiccups in the early stages of development, we must remember that it will be a dynamic process and leave room for change if need be.

In these later weeks we are each assigned a role and we are to work in our field to present a report to the group by week sixteen.  We will shift our focus into taking on these more serious roles and instead of weekly meeting involving the entire group, we will trim them down to a more personalised level.  These 2 or 3 person meetings will help us achieve our goals in a more professional fashion.  It will be up to the lead developer to make regular pulse checks and make changes where needed among the group.

Upon completion of our individual reports, we would be well on our way to having a working prototype, business plans and marketing ideas to help further our endeavours.  At this point we would make the decision if we would like to continue our project as a team or pass it on to those who wish to take the project even further.